## INCOMING
owner | req_id | name | description | objective | status
ACMS | ACMS-REQ-001 | Provide RIO module ET200 in the control cabinet per specification NNN | HVAC shall mount a RIO module ET200 in its control cabinet per specification NNN. | Provide the field I/O backbone for local and remote operation. | implemented
ACMS | ACMS-REQ-002 | Provide local HMI panel in the control cabinet | HVAC shall install a local HMI panel in its control cabinet. | Provide a local operator interface at the HVAC cabinet. | in progress
EMPLOYER | EMP-REQ-002 | Provide local operation functionality of HVAC system in manual mode | HVAC shall support local manual operation independent of SCADA availability. | Ensure operability of HVAC when the remote layer is unavailable. | in progress
OTLAN | OTLAN-REQ-001 | Provide network physical connection point in HVAC control cabinet | HVAC shall provide the physical network connection point inside its control cabinet. | Provide a landing point for OT LAN cabling at the HVAC cabinet. | not started

## OUTGOING
targets | req_id | name | description | objective
ACMS | HVAC-REQ-001 | Provide local operation functionality | ACMS shall provide the local operation functionality requested by HVAC. | Fulfil the local manual operation capability of HVAC.
ACMS | HVAC-REQ-002 | Provide programming and configuration of HMI local panel with RIO module | ACMS shall program and configure the HMI local panel together with the RIO module. | Make the HMI + RIO combination functional for local operation.
OTLAN | HVAC-REQ-003 | Connect the HMI panel to LAN and provide TCP/IP and open ports | OT LAN shall connect the HMI panel to the LAN and provide the required TCP/IP parameters and open ports. | Make the HMI reachable over the OT LAN for diagnostics and engineering.